## Media
PFS Project ACTION Plan
COMPLETE FOR MONTHLY REPORTING
Strategy (Strategy from Table 7.2) | What | Who | When | Process Measure(s) | Date Completed | Collected Process Measures | Notes
MEDIA | Media Subcomittee
MEDIA | Educate Coalition Members on use of state website
MEDIA | a. Hang posters/flyers in high-traffic areas
MEDIA | b. Display table tents in restaurants or other public spaces
MEDIA | c. Insert information into school newsletters or church bulletins
MEDIA | d. Place brochures/flyers in grocery bags
MEDIA | e. Hand out stickers or flyers at school event
MEDIA | f. Provide activity books for kids and resources for parents at PTA meetings
MEDIA | g. Provide public and school libraries with bookmarks for children and parents
MEDIA | h. Place stickers on popcorn bags at local sporting events
MEDIA | i. Participate in community events, such as county fairs or other fundraisers
MEDIA | j. Share Parents Lead conversation starter playing cards in waiting rooms
MEDIA | k. Place coasters in local coffee shops and dining establishments
MEDIA | l. Provide coffee sleeves to local coffee shops and supporting partners who serve the public
MEDIA | m. Purchase billboard space
MEDIA | n. Place media on radio or TV
MEDIA | o. Share information on local cable access channels
MEDIA | p. Utilize free PSA space at local radio stations or host a weekly radio show
MEDIA | q. Submit articles or letters to the editor to the local paper
MEDIA | r. Post or share information on social media
MEDIA | s. Present at teacher in-services
MEDIA | t. Share information during announcements at a church service
MEDIA | u. Promote at community events or meetings
MEDIA | v. Promote social media pages
MEDIA | w. Sign up for email updates in the community section of parentslead.org and share resources with partners

## Parenting Classes
PFS Project ACTION Plan
COMPLETE FOR MONTHLY REPORTING
Strategy (Strategy from Table 7.2) | What | Who | When | Process Measure(s) | Date Completed | Collected Process Measures | Notes
Parenting Supports | Identify Available Resources existing resources in community for parents: Prime for life for parents. Youth Mental Health First Aid Active Parenting
Information Dissemination for Parenting Classes | Information Disseminiation: a. Radio or music streaming service messages (up to $600/month) b. Television or visual streaming service PSAs or advertisements (up to $600/month) c. Printed newspaper or magazine ads (up to $600/month) d. Digital website or search engine ads (up to $600/month) e. Eight customized social media posts/month (up to $300/month) f. Posters hung up throughout community (up to $200/month) g. Flyers handed out to different locations (up to $200/month) h. Presentation to group (up to $400/presentation; maximum $800/month) i. Billboard (up to $1000/month) j. Handing out brochures (up to $200/month) k. Social media live stream (up to $300/video; maximum of $600/month) l. Host a Community Forum or Town Hall Meeting (up to $2,000/event; maximum $4,000/year) m. Host a booth at a community event (up to $200/event; maximum $400/month) n. Meet and share information with key stakeholders (up to $100/meeting; maximum $400/month) o. Attend and share information at a coalition meeting (up to $300/meeting; maximum $600/month) p. Lead a coalition meeting (up to $400/coalition meeting; maximum $800/month) q. Other (preapproved by State)
Enhancing Capacity or Skills (up to $4,000/month) to support your strategy and policy | a. Participate in a webinar (up to $200/webinar; maximum $400/month) b. Host a webinar training (up to $500/webinar; maximum of $1,000/month) c. Attend a conference (up to $750/day; maximum $4,500/year) d. Host a conference (up to $2,000/day; maximum $6,000/year) e. Attend a training (up to $750/day; maximum $9,000/year) f. Host a community training (up to $2,000/day; maximum $8,000/year) g. Host a stakeholder-specific training (up to $500/day; maximum $1,500/month) h. Collection of data from already existing sources related to the environmental change/strategy being implemented i. Collection of new data which will support the environmental change/strategy (up to $3,000 for collection, analysis, j. Evaluation Report (up to $2,000/year) k. Other (preapproved by State)
Providing Support for Parenting Classes | a. Alternative activities i. Creation of an implementation plan (up to $500/plan) ii. Promotion of event (up to $1,000/event; maximum $2,000/month) iii. Implementation of alternative event (up to $1,000/activity; maximum of $2,000/month) b. Evidence-based mentoring program to fidelity i. Creation of an implementation plan (up to $500/plan) ii. Program training for staff (up to $5,000/person) iii. Promotion of program (up to $1,000/program; maximum $2,000/month) iv. Implementation of program (up to $2,000/program; maximum of $4,000/month) c. Evidence-based curriculum i. Creation of an implementation plan (up to $500/plan) ii. Curriculum training for staff (up to $5,000/person) iii. Promotion of curriculum (up to $1,000/curriculum; maximum $2,000/month) iv. Implementation of curriculum (up to $2,000/curriculum; maximum of $4,000/month) d. Implementing an evidence-based screening and brief intervention tool (up to $1,500/month/new location) i. Promotion of new screening tool (up to $900/month) b. Early intervention seminar instruction (Example: DUI/MIP seminars) i. Completion of early intervention instructor training & certification (up to $2,500/person) ii. Promotion of early intervention seminars (up to $1,000/month) c. Implementing parenting classes (Example: Prime for Life for Parents) i. Completion of instructor training (up to $2,500/person) ii. Promotion of parenting classes (up to $1,000/month) e. Other preapproved by State
Enhancing Access/Reducing Barriers (up to $1,000/month) to support your strategy | a. Activities implemented in this category must be preapproved by the state. Reimbursements will be provided based
Changing Consequences (Incentives/Disincentives) (up to $3,000/month) to support your strategy and policy – Increasing or decreasing the probability of a specific behavior that reduces | a. Incentives i. Press release of congratulations (up to $500/month) ii. Award or certificate for doing the right thing (up to $1,000/month) iii. Awards ceremony (up to $3,000/event/year) b. Disincentives i. Press release explaining what is expected (up to $500/release/month) ii. Letters explaining what is expected (up to $500/month) c. Texting Tipline (up to $1,400/year) d. Utilizing Forensic ID Scanners at a community event (up to $200/day, maximum of $1,400/month) e. Utilization of Forensic ID Scanners at a retail establishment (up to $200/month per retail establishment; maximum f. Other preapproved by State
6. Physical Design and Environmental Changes (up to $3,500/month) to support your strategy | a. Permanent or semi-permanent signs or banners (no posters or flyers) built, installed, or erected (up to $1,000/mo i. Example: permanent signage in parks/fair grounds ii. Example: permanent signage in buildings iii. Example: metal signage for community events b. Installation of security cameras as a deterrent or to increase enforcement or prosecution (up to $1,000 for each n c. Reduction in retail/outlet density (up to $3,000/month) d. Other preapproved by State
Modifying/Changing/Implementing Policies – (up to $7,000/month) formal change in written procedures, by-laws, proclamations, rules or laws with written documentation and/or voting procedures | a. Internal policy change (up to $1,500/implementation of new policy; maximum $3,000/month) i. Example: School policy to require evidence-based screening tool to be used. ii. Example: Medical provider/hospital implements new screening tool. b. Procedural changes (up to $1,500/implementation of new procedure; maximum $3,000/month) i. Example: Law enforcement implements new procedure for conducting bar-walkthroughs looking for over-in c. System changes (up to $1,500/implementation of new change; maximum $3,000/month) i. Example: New requirements for obtaining a liquor license (police approval, three strike rule, etc.) ii. Example: New requirements for community events (roped off areas, security, drink sizes, family sections, alc iii. Example: New restrictions/notifications for DUIs. iv. Example: Court requires community service or participation in an evidence-based class. d. Providing support for ordinance change (up to $5,000/implementation of new ordinance; maximum $5,000/mon i. Example: Ordinance requiring Alcohol Server Training. ii. Example: Ordinance requiring alcohol-free community events. iii. Example: Ordinance requiring stricter penalties for alcohol possession, delivery, etc. e. Other preapproved by State

## Trauma Informed Community
PFS Project ACTION Plan
August 2017 - August 2018
COMPLETE FOR MONTHLY REPORTING
Strategy (Strategy from Table 7.2) | What | Who | When | Process Measure(s) | Date Completed | Collected Process Measures | Notes
Trauma Informed Care for Adults
Information Dissemination for Parenting Classes | Information Disseminiation: a. Radio or music streaming service messages (up to $600/month) b. Television or visual streaming service PSAs or advertisements (up to $600/month) c. Printed newspaper or magazine ads (up to $600/month) d. Digital website or search engine ads (up to $600/month) e. Eight customized social media posts/month (up to $300/month) f. Posters hung up throughout community (up to $200/month) g. Flyers handed out to different locations (up to $200/month) h. Presentation to group (up to $400/presentation; maximum $800/month) i. Billboard (up to $1000/month) j. Handing out brochures (up to $200/month) k. Social media live stream (up to $300/video; maximum of $600/month) l. Host a Community Forum or Town Hall Meeting (up to $2,000/event; maximum $4,000/year) m. Host a booth at a community event (up to $200/event; maximum $400/month) n. Meet and share information with key stakeholders (up to $100/meeting; maximum $400/month) o. Attend and share information at a coalition meeting (up to $300/meeting; maximum $600/month) p. Lead a coalition meeting (up to $400/coalition meeting; maximum $800/month) q. Other (preapproved by State)
Enhancing Capacity or Skills (up to $4,000/month) to support your strategy and policy | a. Participate in a webinar (up to $200/webinar; maximum $400/month) b. Host a webinar training (up to $500/webinar; maximum of $1,000/month) c. Attend a conference (up to $750/day; maximum $4,500/year) d. Host a conference (up to $2,000/day; maximum $6,000/year) e. Attend a training (up to $750/day; maximum $9,000/year) f. Host a community training (up to $2,000/day; maximum $8,000/year) g. Host a stakeholder-specific training (up to $500/day; maximum $1,500/month) h. Collection of data from already existing sources related to the environmental change/strategy being implemented i. Collection of new data which will support the environmental change/strategy (up to $3,000 for collection, analysis, j. Evaluation Report (up to $2,000/year) k. Other (preapproved by State)
Providing Support for Parenting Classes | a. Alternative activities i. Creation of an implementation plan (up to $500/plan) ii. Promotion of event (up to $1,000/event; maximum $2,000/month) iii. Implementation of alternative event (up to $1,000/activity; maximum of $2,000/month) b. Evidence-based mentoring program to fidelity i. Creation of an implementation plan (up to $500/plan) ii. Program training for staff (up to $5,000/person) iii. Promotion of program (up to $1,000/program; maximum $2,000/month) iv. Implementation of program (up to $2,000/program; maximum of $4,000/month) c. Evidence-based curriculum i. Creation of an implementation plan (up to $500/plan) ii. Curriculum training for staff (up to $5,000/person) iii. Promotion of curriculum (up to $1,000/curriculum; maximum $2,000/month) iv. Implementation of curriculum (up to $2,000/curriculum; maximum of $4,000/month) d. Implementing an evidence-based screening and brief intervention tool (up to $1,500/month/new location) i. Promotion of new screening tool (up to $900/month) b. Early intervention seminar instruction (Example: DUI/MIP seminars) i. Completion of early intervention instructor training & certification (up to $2,500/person) ii. Promotion of early intervention seminars (up to $1,000/month) c. Implementing parenting classes (Example: Prime for Life for Parents) i. Completion of instructor training (up to $2,500/person) ii. Promotion of parenting classes (up to $1,000/month) e. Other preapproved by State
Enhancing Access/Reducing Barriers (up to $1,000/month) to support your strategy | a. Activities implemented in this category must be preapproved by the state. Reimbursements will be provided based
Changing Consequences (Incentives/Disincentives) (up to $3,000/month) to support your strategy and policy – Increasing or decreasing the probability of a specific behavior that reduces | a. Incentives i. Press release of congratulations (up to $500/month) ii. Award or certificate for doing the right thing (up to $1,000/month) iii. Awards ceremony (up to $3,000/event/year) b. Disincentives i. Press release explaining what is expected (up to $500/release/month) ii. Letters explaining what is expected (up to $500/month) c. Texting Tipline (up to $1,400/year) d. Utilizing Forensic ID Scanners at a community event (up to $200/day, maximum of $1,400/month) e. Utilization of Forensic ID Scanners at a retail establishment (up to $200/month per retail establishment; maximum f. Other preapproved by State
6. Physical Design and Environmental Changes (up to $3,500/month) to support your strategy | a. Permanent or semi-permanent signs or banners (no posters or flyers) built, installed, or erected (up to $1,000/mo i. Example: permanent signage in parks/fair grounds ii. Example: permanent signage in buildings iii. Example: metal signage for community events b. Installation of security cameras as a deterrent or to increase enforcement or prosecution (up to $1,000 for each n c. Reduction in retail/outlet density (up to $3,000/month) d. Other preapproved by State
Modifying/Changing/Implementing Policies – (up to $7,000/month) formal change in written procedures, by-laws, proclamations, rules or laws with written documentation and/or voting procedures | a. Internal policy change (up to $1,500/implementation of new policy; maximum $3,000/month) i. Example: School policy to require evidence-based screening tool to be used. ii. Example: Medical provider/hospital implements new screening tool. b. Procedural changes (up to $1,500/implementation of new procedure; maximum $3,000/month) i. Example: Law enforcement implements new procedure for conducting bar-walkthroughs looking for over-in c. System changes (up to $1,500/implementation of new change; maximum $3,000/month) i. Example: New requirements for obtaining a liquor license (police approval, three strike rule, etc.) ii. Example: New requirements for community events (roped off areas, security, drink sizes, family sections, alc iii. Example: New restrictions/notifications for DUIs. iv. Example: Court requires community service or participation in an evidence-based class. d. Providing support for ordinance change (up to $5,000/implementation of new ordinance; maximum $5,000/mon i. Example: Ordinance requiring Alcohol Server Training. ii. Example: Ordinance requiring alcohol-free community events. iii. Example: Ordinance requiring stricter penalties for alcohol possession, delivery, etc. e. Other preapproved by State

## After School for Middle School
PFS Project ACTION Plan
August 2017 - August 2018
COMPLETE FOR MONTHLY REPORTING
Strategy (Strategy from Table 7.2) | What | Who | When | Process Measure(s) | Date Completed | Collected Process Measures | Notes
Events Targeting Middle Schoolers
Information Dissemination for Parenting Classes | Information Disseminiation: a. Radio or music streaming service messages (up to $600/month) b. Television or visual streaming service PSAs or advertisements (up to $600/month) c. Printed newspaper or magazine ads (up to $600/month) d. Digital website or search engine ads (up to $600/month) e. Eight customized social media posts/month (up to $300/month) f. Posters hung up throughout community (up to $200/month) g. Flyers handed out to different locations (up to $200/month) h. Presentation to group (up to $400/presentation; maximum $800/month) i. Billboard (up to $1000/month) j. Handing out brochures (up to $200/month) k. Social media live stream (up to $300/video; maximum of $600/month) l. Host a Community Forum or Town Hall Meeting (up to $2,000/event; maximum $4,000/year) m. Host a booth at a community event (up to $200/event; maximum $400/month) n. Meet and share information with key stakeholders (up to $100/meeting; maximum $400/month) o. Attend and share information at a coalition meeting (up to $300/meeting; maximum $600/month) p. Lead a coalition meeting (up to $400/coalition meeting; maximum $800/month) q. Other (preapproved by State)
Enhancing Capacity or Skills (up to $4,000/month) to support your strategy and policy | a. Participate in a webinar (up to $200/webinar; maximum $400/month) b. Host a webinar training (up to $500/webinar; maximum of $1,000/month) c. Attend a conference (up to $750/day; maximum $4,500/year) d. Host a conference (up to $2,000/day; maximum $6,000/year) e. Attend a training (up to $750/day; maximum $9,000/year) f. Host a community training (up to $2,000/day; maximum $8,000/year) g. Host a stakeholder-specific training (up to $500/day; maximum $1,500/month) h. Collection of data from already existing sources related to the environmental change/strategy being implemented i. Collection of new data which will support the environmental change/strategy (up to $3,000 for collection, analysis, j. Evaluation Report (up to $2,000/year) k. Other (preapproved by State)
Providing Support for Parenting Classes | a. Alternative activities i. Creation of an implementation plan (up to $500/plan) ii. Promotion of event (up to $1,000/event; maximum $2,000/month) iii. Implementation of alternative event (up to $1,000/activity; maximum of $2,000/month) b. Evidence-based mentoring program to fidelity i. Creation of an implementation plan (up to $500/plan) ii. Program training for staff (up to $5,000/person) iii. Promotion of program (up to $1,000/program; maximum $2,000/month) iv. Implementation of program (up to $2,000/program; maximum of $4,000/month) c. Evidence-based curriculum i. Creation of an implementation plan (up to $500/plan) ii. Curriculum training for staff (up to $5,000/person) iii. Promotion of curriculum (up to $1,000/curriculum; maximum $2,000/month) iv. Implementation of curriculum (up to $2,000/curriculum; maximum of $4,000/month) d. Implementing an evidence-based screening and brief intervention tool (up to $1,500/month/new location) i. Promotion of new screening tool (up to $900/month) b. Early intervention seminar instruction (Example: DUI/MIP seminars) i. Completion of early intervention instructor training & certification (up to $2,500/person) ii. Promotion of early intervention seminars (up to $1,000/month) c. Implementing parenting classes (Example: Prime for Life for Parents) i. Completion of instructor training (up to $2,500/person) ii. Promotion of parenting classes (up to $1,000/month) e. Other preapproved by State
Enhancing Access/Reducing Barriers (up to $1,000/month) to support your strategy | a. Activities implemented in this category must be preapproved by the state. Reimbursements will be provided based
Changing Consequences (Incentives/Disincentives) (up to $3,000/month) to support your strategy and policy – Increasing or decreasing the probability of a specific behavior that reduces | a. Incentives i. Press release of congratulations (up to $500/month) ii. Award or certificate for doing the right thing (up to $1,000/month) iii. Awards ceremony (up to $3,000/event/year) b. Disincentives i. Press release explaining what is expected (up to $500/release/month) ii. Letters explaining what is expected (up to $500/month) c. Texting Tipline (up to $1,400/year) d. Utilizing Forensic ID Scanners at a community event (up to $200/day, maximum of $1,400/month) e. Utilization of Forensic ID Scanners at a retail establishment (up to $200/month per retail establishment; maximum f. Other preapproved by State
6. Physical Design and Environmental Changes (up to $3,500/month) to support your strategy | a. Permanent or semi-permanent signs or banners (no posters or flyers) built, installed, or erected (up to $1,000/mo i. Example: permanent signage in parks/fair grounds ii. Example: permanent signage in buildings iii. Example: metal signage for community events b. Installation of security cameras as a deterrent or to increase enforcement or prosecution (up to $1,000 for each n c. Reduction in retail/outlet density (up to $3,000/month) d. Other preapproved by State
Modifying/Changing/Implementing Policies – (up to $7,000/month) formal change in written procedures, by-laws, proclamations, rules or laws with written documentation and/or voting procedures | a. Internal policy change (up to $1,500/implementation of new policy; maximum $3,000/month) i. Example: School policy to require evidence-based screening tool to be used. ii. Example: Medical provider/hospital implements new screening tool. b. Procedural changes (up to $1,500/implementation of new procedure; maximum $3,000/month) i. Example: Law enforcement implements new procedure for conducting bar-walkthroughs looking for over-in c. System changes (up to $1,500/implementation of new change; maximum $3,000/month) i. Example: New requirements for obtaining a liquor license (police approval, three strike rule, etc.) ii. Example: New requirements for community events (roped off areas, security, drink sizes, family sections, alc iii. Example: New restrictions/notifications for DUIs. iv. Example: Court requires community service or participation in an evidence-based class. d. Providing support for ordinance change (up to $5,000/implementation of new ordinance; maximum $5,000/mon i. Example: Ordinance requiring Alcohol Server Training. ii. Example: Ordinance requiring alcohol-free community events. iii. Example: Ordinance requiring stricter penalties for alcohol possession, delivery, etc. e. Other preapproved by State

## Opioid
PFS Project ACTION Plan
August 2017 - August 2018
COMPLETE FOR MONTHLY REPORTING
Strategy (Strategy from Table 7.2) | What | Who | When | Process Measure(s) | Date Completed | Collected Process Measures | Notes
Opioid Strategies
Information Dissemination for Parenting Classes | Information Disseminiation: a. Radio or music streaming service messages (up to $600/month) b. Television or visual streaming service PSAs or advertisements (up to $600/month) c. Printed newspaper or magazine ads (up to $600/month) d. Digital website or search engine ads (up to $600/month) e. Eight customized social media posts/month (up to $300/month) f. Posters hung up throughout community (up to $200/month) g. Flyers handed out to different locations (up to $200/month) h. Presentation to group (up to $400/presentation; maximum $800/month) i. Billboard (up to $1000/month) j. Handing out brochures (up to $200/month) k. Social media live stream (up to $300/video; maximum of $600/month) l. Host a Community Forum or Town Hall Meeting (up to $2,000/event; maximum $4,000/year) m. Host a booth at a community event (up to $200/event; maximum $400/month) n. Meet and share information with key stakeholders (up to $100/meeting; maximum $400/month) o. Attend and share information at a coalition meeting (up to $300/meeting; maximum $600/month) p. Lead a coalition meeting (up to $400/coalition meeting; maximum $800/month) q. Other (preapproved by State)
Enhancing Capacity or Skills (up to $4,000/month) to support your strategy and policy | a. Participate in a webinar (up to $200/webinar; maximum $400/month) b. Host a webinar training (up to $500/webinar; maximum of $1,000/month) c. Attend a conference (up to $750/day; maximum $4,500/year) d. Host a conference (up to $2,000/day; maximum $6,000/year) e. Attend a training (up to $750/day; maximum $9,000/year) f. Host a community training (up to $2,000/day; maximum $8,000/year) g. Host a stakeholder-specific training (up to $500/day; maximum $1,500/month) h. Collection of data from already existing sources related to the environmental change/strategy being implemented i. Collection of new data which will support the environmental change/strategy (up to $3,000 for collection, analysis, j. Evaluation Report (up to $2,000/year) k. Other (preapproved by State)
Providing Support for Parenting Classes | a. Alternative activities i. Creation of an implementation plan (up to $500/plan) ii. Promotion of event (up to $1,000/event; maximum $2,000/month) iii. Implementation of alternative event (up to $1,000/activity; maximum of $2,000/month) b. Evidence-based mentoring program to fidelity i. Creation of an implementation plan (up to $500/plan) ii. Program training for staff (up to $5,000/person) iii. Promotion of program (up to $1,000/program; maximum $2,000/month) iv. Implementation of program (up to $2,000/program; maximum of $4,000/month) c. Evidence-based curriculum i. Creation of an implementation plan (up to $500/plan) ii. Curriculum training for staff (up to $5,000/person) iii. Promotion of curriculum (up to $1,000/curriculum; maximum $2,000/month) iv. Implementation of curriculum (up to $2,000/curriculum; maximum of $4,000/month) d. Implementing an evidence-based screening and brief intervention tool (up to $1,500/month/new location) i. Promotion of new screening tool (up to $900/month) b. Early intervention seminar instruction (Example: DUI/MIP seminars) i. Completion of early intervention instructor training & certification (up to $2,500/person) ii. Promotion of early intervention seminars (up to $1,000/month) c. Implementing parenting classes (Example: Prime for Life for Parents) i. Completion of instructor training (up to $2,500/person) ii. Promotion of parenting classes (up to $1,000/month) e. Other preapproved by State
Enhancing Access/Reducing Barriers (up to $1,000/month) to support your strategy | a. Activities implemented in this category must be preapproved by the state. Reimbursements will be provided based
Changing Consequences (Incentives/Disincentives) (up to $3,000/month) to support your strategy and policy – Increasing or decreasing the probability of a specific behavior that reduces | a. Incentives i. Press release of congratulations (up to $500/month) ii. Award or certificate for doing the right thing (up to $1,000/month) iii. Awards ceremony (up to $3,000/event/year) b. Disincentives i. Press release explaining what is expected (up to $500/release/month) ii. Letters explaining what is expected (up to $500/month) c. Texting Tipline (up to $1,400/year) d. Utilizing Forensic ID Scanners at a community event (up to $200/day, maximum of $1,400/month) e. Utilization of Forensic ID Scanners at a retail establishment (up to $200/month per retail establishment; maximum f. Other preapproved by State
6. Physical Design and Environmental Changes (up to $3,500/month) to support your strategy | a. Permanent or semi-permanent signs or banners (no posters or flyers) built, installed, or erected (up to $1,000/mo i. Example: permanent signage in parks/fair grounds ii. Example: permanent signage in buildings iii. Example: metal signage for community events b. Installation of security cameras as a deterrent or to increase enforcement or prosecution (up to $1,000 for each n c. Reduction in retail/outlet density (up to $3,000/month) d. Other preapproved by State
Modifying/Changing/Implementing Policies – (up to $7,000/month) formal change in written procedures, by-laws, proclamations, rules or laws with written documentation and/or voting procedures | a. Internal policy change (up to $1,500/implementation of new policy; maximum $3,000/month) i. Example: School policy to require evidence-based screening tool to be used. ii. Example: Medical provider/hospital implements new screening tool. b. Procedural changes (up to $1,500/implementation of new procedure; maximum $3,000/month) i. Example: Law enforcement implements new procedure for conducting bar-walkthroughs looking for over-in c. System changes (up to $1,500/implementation of new change; maximum $3,000/month) i. Example: New requirements for obtaining a liquor license (police approval, three strike rule, etc.) ii. Example: New requirements for community events (roped off areas, security, drink sizes, family sections, alc iii. Example: New restrictions/notifications for DUIs. iv. Example: Court requires community service or participation in an evidence-based class. d. Providing support for ordinance change (up to $5,000/implementation of new ordinance; maximum $5,000/mon i. Example: Ordinance requiring Alcohol Server Training. ii. Example: Ordinance requiring alcohol-free community events. iii. Example: Ordinance requiring stricter penalties for alcohol possession, delivery, etc. e. Other preapproved by State

## Tobacco Plan
PFS Project ACTION Plan
COMPLETE FOR MONTHLY REPORTING
Strategy (Strategy from Table 7.2) | What | Who | When | Process Measure(s) | Date Completed | Collected Process Measures | Notes
Tobacco Plan | tobacco treatment specialists media referrals to physicians
Information Dissemination for Parenting Classes | Information Disseminiation: a. Radio or music streaming service messages (up to $600/month) b. Television or visual streaming service PSAs or advertisements (up to $600/month) c. Printed newspaper or magazine ads (up to $600/month) d. Digital website or search engine ads (up to $600/month) e. Eight customized social media posts/month (up to $300/month) f. Posters hung up throughout community (up to $200/month) g. Flyers handed out to different locations (up to $200/month) h. Presentation to group (up to $400/presentation; maximum $800/month) i. Billboard (up to $1000/month) j. Handing out brochures (up to $200/month) k. Social media live stream (up to $300/video; maximum of $600/month) l. Host a Community Forum or Town Hall Meeting (up to $2,000/event; maximum $4,000/year) m. Host a booth at a community event (up to $200/event; maximum $400/month) n. Meet and share information with key stakeholders (up to $100/meeting; maximum $400/month) o. Attend and share information at a coalition meeting (up to $300/meeting; maximum $600/month) p. Lead a coalition meeting (up to $400/coalition meeting; maximum $800/month) q. Other (preapproved by State)
Enhancing Capacity or Skills (up to $4,000/month) to support your strategy and policy | a. Participate in a webinar (up to $200/webinar; maximum $400/month) b. Host a webinar training (up to $500/webinar; maximum of $1,000/month) c. Attend a conference (up to $750/day; maximum $4,500/year) d. Host a conference (up to $2,000/day; maximum $6,000/year) e. Attend a training (up to $750/day; maximum $9,000/year) f. Host a community training (up to $2,000/day; maximum $8,000/year) g. Host a stakeholder-specific training (up to $500/day; maximum $1,500/month) h. Collection of data from already existing sources related to the environmental change/strategy being implemented i. Collection of new data which will support the environmental change/strategy (up to $3,000 for collection, analysis, j. Evaluation Report (up to $2,000/year) k. Other (preapproved by State)
Providing Support for Parenting Classes | a. Alternative activities i. Creation of an implementation plan (up to $500/plan) ii. Promotion of event (up to $1,000/event; maximum $2,000/month) iii. Implementation of alternative event (up to $1,000/activity; maximum of $2,000/month) b. Evidence-based mentoring program to fidelity i. Creation of an implementation plan (up to $500/plan) ii. Program training for staff (up to $5,000/person) iii. Promotion of program (up to $1,000/program; maximum $2,000/month) iv. Implementation of program (up to $2,000/program; maximum of $4,000/month) c. Evidence-based curriculum i. Creation of an implementation plan (up to $500/plan) ii. Curriculum training for staff (up to $5,000/person) iii. Promotion of curriculum (up to $1,000/curriculum; maximum $2,000/month) iv. Implementation of curriculum (up to $2,000/curriculum; maximum of $4,000/month) d. Implementing an evidence-based screening and brief intervention tool (up to $1,500/month/new location) i. Promotion of new screening tool (up to $900/month) b. Early intervention seminar instruction (Example: DUI/MIP seminars) i. Completion of early intervention instructor training & certification (up to $2,500/person) ii. Promotion of early intervention seminars (up to $1,000/month) c. Implementing parenting classes (Example: Prime for Life for Parents) i. Completion of instructor training (up to $2,500/person) ii. Promotion of parenting classes (up to $1,000/month) e. Other preapproved by State
Enhancing Access/Reducing Barriers (up to $1,000/month) to support your strategy | a. Activities implemented in this category must be preapproved by the state. Reimbursements will be provided based
Changing Consequences (Incentives/Disincentives) (up to $3,000/month) to support your strategy and policy – Increasing or decreasing the probability of a specific behavior that reduces | a. Incentives i. Press release of congratulations (up to $500/month) ii. Award or certificate for doing the right thing (up to $1,000/month) iii. Awards ceremony (up to $3,000/event/year) b. Disincentives i. Press release explaining what is expected (up to $500/release/month) ii. Letters explaining what is expected (up to $500/month) c. Texting Tipline (up to $1,400/year) d. Utilizing Forensic ID Scanners at a community event (up to $200/day, maximum of $1,400/month) e. Utilization of Forensic ID Scanners at a retail establishment (up to $200/month per retail establishment; maximum f. Other preapproved by State
6. Physical Design and Environmental Changes (up to $3,500/month) to support your strategy | a. Permanent or semi-permanent signs or banners (no posters or flyers) built, installed, or erected (up to $1,000/mo i. Example: permanent signage in parks/fair grounds ii. Example: permanent signage in buildings iii. Example: metal signage for community events b. Installation of security cameras as a deterrent or to increase enforcement or prosecution (up to $1,000 for each n c. Reduction in retail/outlet density (up to $3,000/month) d. Other preapproved by State
Modifying/Changing/Implementing Policies – (up to $7,000/month) formal change in written procedures, by-laws, proclamations, rules or laws with written documentation and/or voting procedures | a. Internal policy change (up to $1,500/implementation of new policy; maximum $3,000/month) i. Example: School policy to require evidence-based screening tool to be used. ii. Example: Medical provider/hospital implements new screening tool. b. Procedural changes (up to $1,500/implementation of new procedure; maximum $3,000/month) i. Example: Law enforcement implements new procedure for conducting bar-walkthroughs looking for over-in c. System changes (up to $1,500/implementation of new change; maximum $3,000/month) i. Example: New requirements for obtaining a liquor license (police approval, three strike rule, etc.) ii. Example: New requirements for community events (roped off areas, security, drink sizes, family sections, alc iii. Example: New restrictions/notifications for DUIs. iv. Example: Court requires community service or participation in an evidence-based class. d. Providing support for ordinance change (up to $5,000/implementation of new ordinance; maximum $5,000/mon i. Example: Ordinance requiring Alcohol Server Training. ii. Example: Ordinance requiring alcohol-free community events. iii. Example: Ordinance requiring stricter penalties for alcohol possession, delivery, etc. e. Other preapproved by State